## Sheet1
Punch List
% done | To do | Done | Total
81.33% | 14 | 61 | 75
| Item | State | Details | Status | Location | Legend
1 | Remove old caulk on floor of PR | Done |  | done | PR | BR | Bathroom
2 | Cut off beam under driveway | Done | Cut beam, treat. |  | Ext | PR | Powder room
3 | Fix leaky threshold under the front door | Done |  |  | Foyer | LR | Living room
4 | Trim on shelf in kitchen | Done | The shelf with the Micro wave needs trim added at the ceiling | done | Kitch | DR | Dinning room
5 | Valve and flapper valve in PR | Done |  | done | PR
6 | Valve and flapper valve in Master bath | Done |  | done | MBd
7 | Fireplace doors need to be installed | Done |  | done | LR
8 | Fireplace ceramic pieces need to be replaced | Done |  |  | LR
9 | Remove and plug the spare door bell hole | Done |  | done | Ext
10 | Timer switches on bathroom Fans | Done |  |  | PR
11 | Timer switch on walk-in closet light | Done |  |  | MBd
12 | Smoke alarm | Done | Re install smoke alarm. Is on Smoke alarm compliant with code. | Jim to handle | Hall
13 | Screen on living room window | Done | The screen on the west window of the LR is ripped and needs to be repair |  | LR
14 | Plug hole in LR above speaker | Done |  | done | LR
15 | Sliding glass door in DR |  | The door is very hard to open. |  | DR
16 | Kitchen faucet loose | Done | Water faucet in Kitchen flopping loose in the mounting hole. | Rick to find piece | Kitch
17 | Fireplace mantle match pattern | Done | The end 2 feet of the mantle needs to be removed and replaced with piece that better matches the rest | Rick to call Accent counter | LR
18 | Registers for the heat vents | Done | 4 in the living room - | u r to order- MB is a 4x10 | LR
19 | Puck lights | Done |  | done | LR
20 | Master closet board to be filled | Done | The board with the robe hooks has a saw cut that needs to be filled | done | MBd
21 | Mtr bath closet - Wall board by door to be finished | Done |  |  | MBd
22 | Enlarge holes for faucet - Master bath | Done |  | done | MBd
23 | Enlarge holes for faucet - PR | Done |  | done | PR
24 | Install stair rail downstairs |  |  | Rick to order rails, make newel post | Hall
25 | Cable in Mstr Bedroom | Audio comp | The cable TV cable needs to be put in wall | Audio company - Larry Whitney | MBd
26 | Window sill - entry way | Done |  | done | Foyer
27 | Remove board hanging in tree | Done |  | done- thot it made a nice branch | Ext
28 | Procure switches dimmers and timers | Done | Verify that the electrician is going to buy all this stuff. |  | All
29 | Paint behind outdoor fixtures | Done |  | done | Ext
30 | Install door stop | Done | In the spare bath on wall behind door. |  | Spare Bath
31 | Install sliding door hardware | Done |  | Rick will get these | All
32 | Latice work by front stairs | Done |  |  | Ext
33 | Window sill - Laundry room | Done |  | done | Laund Rm
34 | Office - hole in wall where door knob hit | Done | Small hole in wall | Do not fix if no touch up paint is available. | Office
35 | Install ceiling fan | Done |  | done | MBd
36 | Remove ramp used to move hot tub | Done |  | done | Ext
37 | Connect hot tub | Done |  |  | Ext
38 | Install pickets on east side of driveway | Done |  | done | Ext
39 | Master closet wall paint touch up |  | 5 places to left and right of door |  | MBd
40 | Linen closet door in master bath | Done |  | done | MBd
41 | Install pickets on master BR deck | Done |  | done | MBd
42 | Paint downstairs exterior door on outside | Done |  |  | Ext
43 | Fix Beam under driveway | Done |  |  | Ext
44 | Return air grill in entry way | Done |  |  | Foyer
45 | Replace tub fixture drain and waste | Done | The drain in the bath tub is gold. It needs to be replaced with brushed nickel | camper is on it. | MBd
46 | Paint vanity | Done | It is painted, we need the drawers installed |  | MBd
47 | Put sample colors on door | Done |  | simpson is on it | Ext
48 | Marble shelf for platform on cherry panel |  |  | Accent counter is making this | LR
49 | Right TV cabinet door does not close flush | Done | When you press the door the magnectic catch does catch |  | LR
50 | Carpet in MB bath | Done |  |  | MBd
51 | Carpet in family room | Done |  |  | FR
52 | Carpet in ugly door | Done |  |  | Kitch
53 | Trim strip on vanity in MB bath | Done | Not needed |  | MBd
54 | Toe kick in PR is not fastened in place | Done |  |  | PR
55 | Scratches on Kitchen floor | Done | These appeared after the wine fridge was moved. |  | Kitch
56 | The MB shower drains very slowly | Done
57 | Install Drawer and closet Pulls in MB bath |  | Lloyd and Sylvia will get these. They are on order | On Order
58 | Install bookshelves in Family room | Done
59 | Fix Hole in wall in MB below LH wall speaker | Done
60 | Touch up patch behind office door |  |  | Needs Paint
61 | Install dimmer on Stair well | Done
62 | Replace broken globe | Done | Light in MB | Ready to be picked up
63 | Fill Gap behind light over fountain | Done
64 | Exterior light doesn't work and not aimed correctly | Done
65 | The Stairwell light need a dimmer | Done
66 | Two nicks on new floor in doorway to PR | Done | Can't fix
67 | The floor in the family Room squeeks
68 | Install front door hardware | Done | HW is in | HW is in and in the foyer
69 | Install door brush under down stairs door | Done
70 | Install TP & towel rack in MB bath |  | New part is ready to be installed | Has been re-ordered
71 | Touch up paint on Front door
72 | Adjust sliding screen on DR door |  | The screen is to loose. The screen door does not slide freely.
73 | Install Cylinder in garage pedestrian door
74 | Metal braid to be installed on track lighting
75 | cover gap between shelf and wall on top of shelf |  | The top of the book shelf if open. Items can fall between the wall and the bookshelf